Select any team name you prefer.
Please enter your name as it appears in Canvas.
This is the priority ranking for this feature, relative to all other features.

Lower integers are higher in prioirty.

The customer may add or (for unimplemented features) remove features and change priority rankings at the start of each sprint.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
        Select "Completed Day 1" if finished on the first day, and
        similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
        Select "Completed Day 1" if finished on the first day, and
        similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
        Select "Completed Day 1" if finished on the first day, and
        similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
        Select "Completed Day 1" if finished on the first day, and
        similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
        Select "Completed Day 1" if finished on the first day, and
        similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
## Product Backlog
Project Name	School Management And Reporting Tool (SMART)
Product Name:	SMART Suggested Solution					Complete Fields in Green!!!
Team ID:	Suggested Solutions Я Us					Product Backlog Burn Chart / Sprints / Features Remaining at end of Sprint

	Team Member Name					Initials	Student ID
Required	Utsav KC					UK	1001733635

Sprint #	Remaining	Completed This Sprint				Comment
0	27				Total	Total number of features (in column H)
1	22	5			1	Total features left at the end of Sprint #1
2	16	6			2	Total features left at the end of Sprint #2
3	11	5			3	...and so on
4	8	3
5	5	3
6	2	3

©2016-2021 by George F. Rice
This work is licensed under a Creative Commons Attribution 4.0 International License.						Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
						Additional features may be proposed by the student but must be approved by the Product Owner in writing
						Features
Feature ID	Priority	Required	Bonus	Est	Planned	Status	As a(n)…	I want to...	So that I can…	Notes
PERSON	1	1		13	1	Finished in Sprint 1	Administrator	Track people’s names and email addresses	Find and contact them	Need a Person base class with to_string / operator<< name and a full_info method
STUDENT	2	1		8	1	Finished in Sprint 1	Administrator	Track students by grade	Verify students’ progress	Need a Student derived class that includes the grade level (1-12)
PARENT	3	1		3	1	Finished in Sprint 1	Administrator	Track parents	Coordinate on student progress	Need a Parent derived class
RELATE	4	1		5	1	Finished in Sprint 1	Administrator	Associate each student with parents bidirectionally	Know which parents to contact	Mutual aggregate relationship
CLI	5	1	25	13	1	Finished in Sprint 1	Administrator	Basic command line user interface	Verify the system before moving to a GUI	This is cli.cpp for sprint 1 only (optional for bonus points)
WINDOW	6	2		13	2	Finished in Sprint 2	All	Use a windowed rather than command line interface	Use SMART more intuitively	Create a main window with a menu bar, data area, and status bar
D_STUDENT	7	2		8	2	Finished in Sprint 2	Administrator	Create students via dialogs	Conveniently enter the data	Series of dialogs, one per constructor parameter, is OK
DISPLAY	8	2		5	2	Finished in Sprint 2	Teacher	See all current data in the main window	Keep up with students	Display full_info for students and parents in a table in the data area
D_PARENT	9	2		5	2	Finished in Sprint 2	Administrator	Create parents via dialogs	Conveniently enter the data	Series of dialogs, one per constructor parameter, is OK
D_RELATE	10	2		8	2	Finished in Sprint 2	Administrator	Relate students to parents via dialogs	Conveniently enter the data	Dialog listing students and entering index, then same for parents
NEW	11	2		2	2	Finished in Sprint 2	Administrator	Clear all data	Start a new school	Simply clear all elements from the vectors
SAVE	12	3		13	3	Finished in Sprint 3	All	Write the data to persistent storage	Don’t have to re-enter data	See Lecture 15 for an object-oriented strategy to create the file format
LOAD	13	3		8	3	Finished in Sprint 3	All	Load data for a school from persistent storage	Don’t have to re-enter data	Select file via a file chooser dialog
SAVEAS	14	3		8	3	Finished in Sprint 3	Administrator	Save data to a different filename	Create backups or baselines for new schools	Select filename via a file chooser dialog
TOOLBAR	15	3		5	3	Finished in Sprint 3	All	Use the major features via a toolbar	Point and click	Suggest using the Nim game’s toolbar as a baseline
ABOUT	16	3		1	3	Finished in Sprint 3	Administrator	Display an About dialog with creator and version	Quickly determine which version is installed	Use Gtk::AboutDialog
COURSE	17	4		21	4	Finished in Sprint 4
SEMESTER	18	4		8	4	Finished in Sprint 4
SECTION	19	4		5	4	Finished in Sprint 4
	20
	21
	22
SUBJECT	23	5			5	Finished in Sprint 5
TEACHER	24	5		21	5	Finished in Sprint 5
GRADE	25	5		5	5	Finished in Sprint 5
TRANSCRIPT	26	5		8	5	Finished in Sprint 5
ITERATORS	27	5		8	5	Finished in Sprint 5

						BONUS WORK – COMPLETE ABOVE FEATURES FIRST!!!

## Sprint 01 Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Mar 02		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Mar 09		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	13
Day 1 Left	10	3
Day 2 Left	10	0
Day 3 Left	3	7
Day 4 Left	1	2
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	0	1

Task ID	Feature ID	Assigned To	Task	Status	Notes
1	PERSON		Code person.h	Completed Day 1
2	PERSON		Code person.cpp	Completed Day 1
3	PERSON		Test compile Person class	Completed Day 1
4	STUDENT		Code student.h	Completed Day 3
5	STUDENT		Code student.cpp	Completed Day 3
6	STUDENT		Test compile Student class	Completed Day 3
7	PARENT		Duplicate Student to Parent	Completed Day 3
8	PARENT		Remove grade, update to_string() and full_info()	Completed Day 3
9	PARENT		Test compile Parent class	Completed Day 3
10	RELATE		Build with example code and verify	Completed Day 3
11	CLI		(Bonus) Write CLI	Completed Day 4
12	CLI		(Bonus) Test CLI	Completed Day 4
13	CLI		(Bonus) Fix (work-around) vector reallocation bug	Completed Day 7
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint #	2		Complete Fields in Green!!!
Start on	Mar 09		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Mar 23		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	13
Day 1 Left	13	0
Day 2 Left	7	6
Day 3 Left	5	2
Day 4 Left	5	0
Day 5 Left	4	1
Day 6 Left	3	1
Day 7 Left	0	3
			ADD tasks below to complete each feature for THIS sprint
Task ID	Feature ID	Assigned To	Description	Status	Notes
1	WINDOW		Baseline main.cpp from nim	Completed Day 2
2	WINDOW		Update Makefile for gtkmm	Completed Day 2
3	WINDOW		Baseline Mainwin class from nim	Completed Day 2
4	D_STUDENT		Baseline EntryDialog class from Lecture 14	Completed Day 2
5	WINDOW		Create menu for SMART in Mainwin class	Completed Day 2
6	DISPLAY		Add display label, vectors, and show_data method	Completed Day 2
7	D_STUDENT		Write on_new_student_click using EntryDialog	Completed Day 3
8	D_PARENT		Write on_new_parent_click using EntryDialog	Completed Day 3
9	D_RELATE		Write on_student_parent_click using EntryDialog	Completed Day 5
10	WINDOW		Add Easter egg to support testing and demos	Completed Day 7
11	WINDOW		Refactor: select, select_student, and select_parent methods	Completed Day 7
12	WINDOW		Test and improve error handling	Completed Day 6
13	WINDOW		Backport bug fixes from P07	Completed Day 7
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Mar 23		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Mar 30		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	0
Day 1 Left	0	0
Day 2 Left	0	0
Day 3 Left	0	0
Day 4 Left	0	0
Day 5 Left	0	0
Day 6 Left	0	0
Day 7 Left	0	0
			ADD tasks below to complete each feature for THIS sprint
Task ID	Feature ID	Assigned To	Description	Status	Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint #	4		Complete Fields in Green!!!
Start on	Apr 06		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Apr 13		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	0
Day 1 Left	0	0
Day 2 Left	0	0
Day 3 Left	0	0
Day 4 Left	0	0
Day 5 Left	0	0
Day 6 Left	0	0
Day 7 Left	0	0
			ADD tasks below to complete each feature for THIS sprint
Task ID	Feature ID	Assigned To	Description	Status	Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint #	5		Complete Fields in Green!!!
Start on	Apr 13		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Apr 20		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	0
Day 1 Left	0	0
Day 2 Left	0	0
Day 3 Left	0	0
Day 4 Left	0	0
Day 5 Left	0	0
Day 6 Left	0	0
Day 7 Left	0	0
			ADD tasks below to complete each feature for THIS sprint
Task ID	Feature ID	Assigned To	Description	Status	Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84